## Sheet1
ESTIMATES
Requirements Gathering |  |  |  | 1 week
| Identifying the users |  | : |  | 1 day
| Identifying the user group |  |  |  | 1 day
| Identifying possible inputs |  |  |  | 2days
| Identifying possible output |  |  |  | 1day
| Analyzing the validity of the requirements |  |  |  | 2days
35hrs
design |  |  |  | 1 week
| identifying the software ,hardware and system requirements |  |  |  | 1 day
| identifying the system specifications that server the inputs |  |  |  | 1day
| develop a test strategy |  |  |  | 2 days
| define a system architecture |  |  |  | 3days
35hrs
Implementation/coding |  |  |  | 4 and a half weeks
| installing the softwares |  |  |  | 4days
| Dividing the work into modules |  |  |  | 1day
Actual coding/development
| Developing the modues |  |  |  | 2weeks
| Integrating the modules |  |  |  | 6days
125hrs
Testing |  |  |  | 2 weeks
| Unit testing |  |  |  | 4days
| Funtional Testing |  |  |  | 3days
| Integration Testing |  |  |  | 6days
70hrs
Deployment |  |  |  | 1 week
| Beta test |  |  |  | 3days
| Bug fixes |  |  |  | 4days
310hrs